## PROJECT PLAN
Moki Website Redevelopment |  |  |  |  | Update 3.3.15
Phase One - B2B PORTAL
TASK # | PRIORITY | ACTIVITY | STAFF | COMPLETE | COMMENTS
A |  | Project set-up
A.1 | 1 | Deactivate Portal | Andrea | Complete | Portal currently inactive on website
A.2 | 1 | Check if any customers registered for online access since the launch of the website | Annexa / Tracey |  | Annexa to provide a report to Tracey on all customers who registered through the portal since launch. Tracey to then then analys.
Templates/layouts
A.3 | 1 | Create design/layouts for all webpages | Karen
A.4 | 2 | Create layout for new auto-generated PDF product guide | Karen
A.5 | 4 | Create layouts for new email templates | Karen
Work flow process mapping
A.6 | 1 | Design work flow for online orders by Local Retailers (free shipping) | ALL
A.7 | 1 | Design work flow for online orders by International Retailers (free shipping) | ALL
A.8 | 1 | Design work flow for online orders by Local Retailers (pro-rata shipping costs) | ALL
A.9 | 1 | Design work flow for online orders by International Distributors (Shipping payable) | ALL
A.10 | 1 | Design work flow for 15% online orders processing | ALL |  | 15% off pertains to online order for independent etailersonly
A.11 | 2 | Design work flow process for online customer registration | ALL |  | Customer completes online credit application form > Email sent to tracey > Tracey checks for duplicates > Tracey approves > Login details automatically generated > Login details automatically emailed to customer
A.12 | 1 | Design work flow process for password recovery | ALL
A.13 | Phase 3 | Design work flow process for Credit Applications | ALL | Moved to Phase 3
A.14 | 4 | Design work flow process for email marketing campaigns/templates | ALL
A.15 | 2 | Design work flow process for creating the Product Catalogue online | ALL |  | Accessible to Staff only. Generates PDF.
B |  | Customer & Netsuite Data
Customer Data validation
B.1 | 1 | Create a checklist for checking customers have correct information in Netsuite | Tracey |  | Checklist to be used when checking each customer record
B.2 | 1 | Complete customer data validation | ALL - Tracey to delegate
Customer status
B.3 | 1 | Setup Retail Lead & Customer groups in Netsuite | Tracey | Complete | Created
B.4 | 1 | Setup Distributor Lead & Customer groups in Netsuite | Tracey | Complete | Created
B.5 | 1 | Confirm lead to customer status conversion - Retail | Tracey / Annexa (script) | Complete | Annexa to write script
B.6 | 1 | Confirm lead to customer status conversion - Distributor | Tracey / Annexa (script) | Complete | Annexa to write script
B.7 | 1 | Confirm correct customer status of existing customers | ALL - Tracey to delegate
Eligible for 15% discount online
B.8 | 1 | Add checkbox to customer record to indicate whether customer is/isn't eligible for 15% discount | Tracey |  | Tick box added to Web Tab on customer record
Inventory available
B.9 | 4 | Add checkbox to customer record to indicate whether they can see product inventory | Tracey |  | Tick box"Show Stock Level" added to Web Tab on customer record
Free delivery rules in Netsuite
B.10 | 1 | Add Free Delivery threshold to Customer Record (checkbox or field) | Tracey
B.11 | 1 | Implement free delivery rules for online orders for local retailers. | Annexa |  | Australian & NZ Retail: Free shipping over pre-determined amount. Order automated to warehouse.
B.12 | 1 | Implement paid delivery rules for online orders for remote local retailers (specific postcodes/customers). | Annexa |  | Australian & NZ Retail (remote): Freight = 10% order value. Order to be confirmed by accounts team. A checkbox has been added to the customer record "Freight Approval Required"
B.13 | 1 | Implement free delivery rules for online orders for international retailers. | Annexa |  | International Retail: Free shipping. Order to be confirmed by accounts team/Andrea. International distributors: Freight = case-by-case basis. Order to be confirmed by accounts team/Andrea.
B.14 | 1 | Implement paid delivery rules for online orders for international distributors | Annexa |  | A checkbox has been added to the customer record "Freight Approval Required"
RRP lists in Netsuite - general public
B.15 | 1 | Add Australian RRP price list to Netsuite | Tracey |  | Tracey to load in as a price price level AUSTRALIAN RRP in Netsuite
B.16 | 1 | Add NZ RRP price list to Netsuite | Tracey |  | Tracey to load in as a price price level NZ RRP in Netsuite
B.17 | 1 | Add USA RRP price list to Netsuite | Tracey |  | Tracey to load in as a price price level USA SRP in Netsuite
B.18 | 1 | Add Canadian RRP prices list to Netsuite | Tracey |  | Tracey to load in as a price price level CANADA SRP in Netsuite
B.19 | 1 | Add South African RRP price list to Netsuite | Tracey |  | Tracey to load in as a price price level SOUTH AFRICAN RRP in Netsuite
B.20 | 1 | Add UK RRP price list to Netsuite | Tracey |  | Tracey to load in as a price price level UK RRP in Netsuite
New Inventory Item
B21 | 2 | Add "Staff only" checkbox to inventory item | Tracey
C |  | Pricing on the website for general public view - NOT LOGGED IN
Displayed prices
C.1 | 1 | Website localises RRP prices based on location | Annexa |  | All international sites are currently showing AUD.
C.2 | 1 | Wesbite indicates currency based on location | Annexa |  | Eg. USD, AUD, CAD etc
C.3 | 2 | Website indicates "RRP or SRP" next to price | Annexa |  | "SRP" is USA and Canada only.All others use RRP
ONLINE ORDERING - Refer to page layouts for individual page design and layout
D |  | Username and password setup
Username and passwords for existing customers
D.1 | 1 | Username and password storage | Annexa |  | Annexa to provide guidance and delevlop back-end for this process. Email address for contact to be validated during previous customer data validation task
D.2 | 1 | Generate passwords for all existing customers | Annexa
Username and passwords for new registering customers
D.3 | 1 | Implement username and password generation | Annexa |  | Annexa to provide guidance and delevlop back-end for this process. See process map.
D.4 | 2 | Implement process to prevent email registration duplicates | Annexa |  | Provide Mokie with staff instuctions
Forgotten passwords
D.5 | 1 | Automate forgotten password process | Annexa |  | Annexa to provide guidance and delevlop back-end for this process.
E |  | Customer log in
Login drop-down box
E.1 | 4 | Rename "Become a reseller link" to "Register for online ordering" | Andrea
F |  | Welcome page
Page design
F.1 | 3 | Name of user appears when logged in | Annexa |  | Tracey to register and test
F.2 | 4 | Modify wording in middle banner to welcome user | Karyn & Amy
F.3 | 1 | Add "15% discount (before freight)" banner that is viewable to certain customers only | Karyn & Amy / Annexa |  | Tracey has added tick box to customers who are eligible for special.
G |  | Customer Order page
Customer-specific pricing
G.1 | 1 | Individual customer pricing appears | Annexa
G.3 | 1 | RRP or SRP appears next to price | Annexa |  | "SRP" is USA and Canada only.All others use RRP
G.4 | 1 | Correct currency for each customer | Annexa |  | Currently showing USD only
Page design
G.5 | 3 | Rename page from "Quick Order" to "Place order" | Andrea
G.6 | 4 | Modify wording in middle banner to reflect ordering instructions | Karyn & Amy
G.7 | 1 | Fix "Go To Checkout" link | Annexa |  | Currently not working
G.8 | 2 | Add "free delivery" countdown for applicable local retail customers | Annexa |  | "Spend $$ more for free delivery".
G.9 | 3 | Product information (when clicking product link) opens in same window and retains log-in | Annexa
G.10 | 1 | Add "15% discount (before freight)" image somewhere on the page that is viewable to certain customers only | Karyn & Amy / Annexa |  | Tracey has added tick box to customers who are eligible for special.
G.11 | 1 | Add "minimum quantity 10,000" next to Tommy and Drops | Karyn & Amy
Inventory available
G.12 | 4 | Enable select customers to see current inventory levels of products (position near price) | Annexa
New products - visible to staff only
G.13 | 2 | Add new products - visible to staff logins only | Tracey / Annexa |  | Tracey to create checkbox on Inventory items "Product viewable by staff only"
H |  | View Cart page
Page design
H.1 | 2 | Add "free delivery" countdown notification (see G.8) | Annexa
H.2 | 1 | Fix "Go To Checkout" link | Annexa |  | Currently not working
H.3 | 1 | Fix "Continue shopping" link | Annexa |  | Currently not working
H.4 | 3 | Add "Back" button | Annexa
H.5 | 4 | Make "X" slightly larger (to delete item from cart) | Karyn |  | Currently hard to see
I |  | Checkout page
Page design
I.1 | 1 | Remove shipping options page | Annexa
I.2 | 1 | Integrate payment options | Annexa |  | Payment is through invoice, credit card and direct deposit. PayPal only for Phase 2
I.3 | 4 | Add "Store details for next visit" tick box for customer use | Annexa
I.4 | 1 | Apply 15% discount to order for select customers | Annexa |  | Tracey has added tick box to customers who are eligible for special. Apply a 15% discount to total order ex GST.
I.5 | 1 | Check all taxes are calculated correctly based on international location | Annexa |  | International distros: 0% tax
I.6 | 4 | Add FAQ link to "Need Help?" | Andrea |  | Replace "Contact Us"
I.7 | 1 | Add text: "By clicking submit you are confirming your order in accordance to your existing trading terms with Moki International" | Andrea |  | Confirm with Legal
I.8 | 3 | Add "Back" button | Annexa
J |  | Order Complete page
Page design
J.1 | 1 | Show "Sales Order" number for order and refine confirmation text | Annexa |  | Display the automated Sales Order number
J.2 | 3 | Add "Print" button to print the page with SO number | Annexa |  | Add a link to download and print the SO
J.4 | 4 | Remove "continue browing button" | Annexa
J.5 | 4 | Remove "Exit Moki" button | Annexa
Email confirmation
J.6 | 1 | Send an automated email to customer with SO number (not attachment) | Annexa
Billing through Netsuite
J.7 | 1 | Centrally billed customers - ensure invoice is going to parent company | Tracey
Invoice is emailed to the customer when order is marked as "Billed", except for customers with "Freight Approval Required"
K |  | Individual product pages - logged in
K.1 | 3 | Add "Buy Now" button and qty box | Annexa |  | Allow customer to add a product to their cart from the product pages. Karyn to design layout of button and positioning.
K.2 | 3 | Add specific customer purchase pricing alongside RRP | Annexa |  | Show the individual wholesale/dist.price of the product next to the existing RRP price
K.3 | 3 | Add sizing to the speakers product pages | Annexa / Amy |  | Added to the specs list.Need to investigate which section of the code needs to be adjusted.
K.4 | 4 | Add "New" image to new products | Karyn & Amy |  | All new products will be listed as new for 3 months
K.5 | 1 | Add "RRP" or "SRP" to the front of the RRP prices on each product page | Annexa
K.6 | Phase 3 | Add 360 degree photos of each product | Richard / Amy | Moved to Phase 3 | To be updated slowly over time
L |  | FAQ page
FAQ page - logged in
L.1 | 2 | Ordering specific questions appear when logged in only | Annexa / Karyn |  | Annexa to program / Karyn to provide Q's.
FAQ page - general public
L.2 | 4 | Organise questions into categories | Karyn & Amy
L.3 | 4 | Update FAQ with incoming enquiries | Tracey / Karyn & Amy
OTHER WEBSITE REQUIREMENTS
M |  | Other General Moki website changes
Menu items - general public
M.1 | 1 | Remove 'Resellers' link from bottom menu | Andrea | Complete | Currently hidden in FOOTERHTML tag
M.2 | 2 | Rename LOGIN link to "CUSTOMER LOG-IN" | Andrea |  | Use Website theme
M.3 | 1 | Add cart icon to the top of the page | Annexa |  | Does Annexa have a vector/code of the cart image or do we need to supply? Karyn to design layout of where to position for Annexa.
M.4 | 4 | Change search bar to drop down box and magnifying glass | Annexa |  | Does Annexa have a vector/code of the magnifying glass image or do we need to supply? Karyn to design layout for Annexa.
Menu items - logged in
M.5 | 3 | Rename button "Quick Order" to "Place order" | Andrea
M.6 | 1 | Disable "My Account" menu/pages until Phase 2 | Annexa
M.7 | 1 | Activate product menu drop-downs | Annexa
M.8 | 2 | Add "PDF" link to top menu that is visible to staff only | Annexa
New pages
M.9 | 4 | Add new pages Distributor, Retailer | Andrea | Complete | Use FOOTERHTML tag
M.10 | Phase 3 | Add new pages , Where to buy | Andrea | Moved to Phase 3
M.11 | Phase 3 | Add Distributor information pack to Distributor page | Andrea | Moved to Phase 3
M.12 | Phase 3 | Develop plan for "News" page | TBA | Moved to Phase 3 | Leave until Phase 3
Search results
M.13 | 4 | Modify search results layout | Karyn?
Contact Us
M.14 | 4 | Remove "+" from emails send via Moki online forms | Annexa |  | Currently emails sent through our online forms appear: My+name+is+….
Analytics
M.15 | Phase 3 | Ensure all "marketing" data is being captured in Netsuite for each customer | Annexa | Moved to Phase 3 | Customer record > Marketing
M.16 | 3 | Integrate google analytics | Annexa
Current Products to add
M.17 | 1 | Add remaining Popper headphones | Amy |  | Training required
Moki homepage
M.18 | Phase 3 | Make "Available at" animated bar country specific | Annexa | Moved to Phase 3 | Currently the Australian site is showing links to US retailers. Please make country specific.
M.19 | 4 | Update links on "Available at" animated bar on home page to go to Moki search results on external sites | Karyn / Andrea |  | Modify in HOMELOGOS tag. Andrea to send list of companies to Karyn.
N |  | Credit Application online form
N.1 | Phase 3 | Cost integrating a credit application form to the website | Annexa | Moved to Phase 3
N.2 | Phase 3 | Confirm with Legal requirements of legally binding document | Andrea | Moved to Phase 4
N.3 | Phase 3 | Re-design registration form to include Credit Application fields | Annexa | Moved to Phase 5
EMAIL MARKETING
O |  | Email marketing
O.1 | 4 | Create email templates in HTML for each customer category | Karyn & Amy / Annexa
O.2 | 4 | Check/establish the mailing list groups | Karyn & Amy / Tracey |  | May require Tracey to add another feild to the customer record to assign contact to group.
PRODUCT GUIDE
P |  | Online generation of Product Guide PDF
P.1 | 2 | Migrate product guide to online format that downloadable (.pdf) and printable. Available to staff only | Annexa